## START
FICTIONAL EXAMPLE — FOR DEMONSTRATION ONLY
REGULATION 45 REVIEW TOOLKIT
Regulation 45 Review Toolkit
| REVIEW DETAILS |  | QUICK ACTIONS
| Review period start | 2026-01-01 | Open Dashboard →
| Review period end | 2026-06-30 | Plan Review →
| Date review started | 2026-07-06 | Review Evidence →
| Target completion date | 2026-08-31 | Record Views →
| Actual completion date |  | Analyse Findings →
| Review reference |  | Manage Actions →
Prepare Report →
| HOME DETAILS |  | HOW TO USE THIS WORKBOOK
| Children's home | Willow House | 1 Set up your review in the card on the left.
| Ofsted URN | 9999999 | 2 Choose review areas on REVIEW PLAN.
| Provider | Example Care Group Ltd | 3 Log the evidence you consider on EVIDENCE.
| Registered Manager | Sarah Example | 4 Capture stakeholder themes on VIEWS.
| Responsible Individual | Alex Example | 5 Record what the evidence means on FINDINGS.
| Review lead | Sarah Example | 6 Agree and track actions on ACTIONS.
7 Bring it together on REPORT.
| These details are stored only in this copy of the workbook. |  | More free care tools · Get free tool updates →
YOUR REVIEW WORKFLOW
1 Plan → 2 Evidence → 3 Views → 4 Findings → 5 Actions → 6 Report
🔒 Your review stays within this workbook. Nothing entered here is transmitted to us. Save it wherever your organisation keeps management records.
Version 1.0.0 · Released August 2026 · Works in Excel 2010 or later · No macros
Independent management-support resource. Not produced, approved or endorsed by Ofsted; does not replace professional judgement.

## DASHBOARD
FICTIONAL EXAMPLE — FOR DEMONSTRATION ONLY
REGULATION 45 REVIEW TOOLKIT |  |  |  | ← Start
Regulation 45 Review
| Evidence reviewed | Views represented | Findings | Open actions
REVIEW WORKFLOW
Review setup
Review plan
Evidence
Views
Findings
Report
ACTIONS REQUIRING ATTENTION
| Action | Owner | Due | Status
FINDINGS OVERVIEW
| Strengths | Areas for improvement | Further review required
STAKEHOLDER VIEWS
Children
Parents / Carers
Placing Authorities / Professionals
Staff
This dashboard shows workflow progress only. It is not a score, a grade, or a judgement about the quality of care.
Toolkit version 1.0.0 · Works in Excel 2010 or later · No macros

## REVIEW PLAN
FICTIONAL EXAMPLE — FOR DEMONSTRATION ONLY
REGULATION 45 REVIEW TOOLKIT |  |  |  | ← Dashboard
Review Plan
Decide what this review needs to focus on. Not every area needs reviewing every cycle — pick what matters this period.
Review area | Why review this? | Evidence to consider | Responsible role | Status
Children's experiences | Follow up themes raised in children's meetings | Children's meetings; complaints; key-work themes | Registered Manager | Reviewed
Behaviour / support | Incident levels compared with the previous period | Incident trends; restraint records | Deputy Manager | Reviewed
Staffing | Evening cover and reliance on agency staff | Rotas; Regulation 44 reports; staff feedback | Registered Manager | In progress
Education | Attendance and placement stability | Attendance themes; PEP-related themes | Registered Manager | In progress
Health | Completion of routine health checks | Health outcomes; medication themes | Deputy Manager | Reviewed

## EVIDENCE
FICTIONAL EXAMPLE — FOR DEMONSTRATION ONLY
REGULATION 45 REVIEW TOOLKIT | [5 empty] | ← Dashboard
Evidence
Record what was considered and the management-level finding. Avoid duplicating confidential case information unnecessarily — reference it, don't copy it.
Evidence category | Evidence source | Review period | Reviewed? | Key management finding | Follow-up required? | Linked finding ID
Quality Assurance | Regulation 44 reports | Jan–Jun 2026 | Yes | Visits completed each month. Recurring theme around evening staffing cover. | Yes | F-003
Quality Assurance | Previous Regulation 45 action plan | Jan–Jun 2026 | Yes | Four of five previous actions completed; garden refurbishment carried forward. | No
Children's Experiences | Children's meetings | Jan–Jun 2026 | Yes | Children asked for more say in weekend activity planning. | Yes | F-004
Children's Experiences | Complaints | Jan–Jun 2026 | Yes | One complaint received and resolved; learning shared with the team. | No
Safeguarding | Safeguarding themes | Jan–Jun 2026 | Yes | No new referrals this period; monitoring continues. | No
Safeguarding | Missing-from-care themes | Jan–Jun 2026 | Yes | Two short episodes, both followed procedure; return interviews completed. | No
Behaviour / Support | Incident trends | Jan–Jun 2026 | Yes | Incidents down from 14 to 8 versus the previous period; fewest on evenings with familiar staff. | Yes | F-002
Health | Health outcomes | Jan–Jun 2026 | Yes | All routine checks up to date; one dental appointment outstanding. | Yes | F-006
Education | Attendance themes | Jan–Jun 2026 | Yes | Attendance improved for two children; one placement remains fragile. | Yes | F-005
Staffing | Supervision | Jan–Jun 2026 | Yes | Supervisions on schedule; quality of recorded reflection varies. | No
Staffing | Agency use | Jan–Jun 2026 | No |  | No
Quality Assurance | Internal audits | Jan–Jun 2026 | No |  | No

## VIEWS
FICTIONAL EXAMPLE — FOR DEMONSTRATION ONLY
REGULATION 45 REVIEW TOOLKIT | [5 empty] | ← Dashboard
Stakeholder Views
Themes from children, parents/carers, placing authorities and staff. Record themes, not names — no individual needs to be identified here.
Stakeholder group | Date / period | Method | Theme | Summary / finding | Classification | Action required?
Children | Mar 2026 | Children's meeting | Activity planning | Children want more involvement in choosing weekend activities. | Improvement theme | Yes
Children | May 2026 | Key-work discussion | Feeling settled | Two children describe the home as calm and say they feel listened to. | Positive theme | No
Parents / Carers | Apr 2026 | Telephone feedback | Communication | Parents value the weekly updates; one asked for earlier notice of appointments. | Mixed | No
Staff | Feb 2026 | Team meeting | Evening staffing | Staff report evenings feel stretched when agency cover is used. | Improvement theme | Yes
Staff | Jun 2026 | Survey | Training | The team feels recent de-escalation training has helped day-to-day practice. | Positive theme | No

## FINDINGS
FICTIONAL EXAMPLE — FOR DEMONSTRATION ONLY
REGULATION 45 REVIEW TOOLKIT | [8 empty] | ← Dashboard
Findings
Evidence alone isn't a review — record what it appears to mean. Classify each finding as a strength, an area for improvement, or something needing further review.
Finding ID | Review area | Finding | Evidence considered | Children's experience / impact | Outcomes / development impact | Classification | Action required? | Action created? | Check
| Children's experiences | Children describe the home as calm and report feeling listened to. | Children's meetings; key-work themes | Children present as settled and engaged in home life. | Supports emotional security and stability. | Strength | No
| Behaviour / support | Incidents have reduced markedly and are lowest when familiar staff cover evenings. | Incident trends; Regulation 44 reports | Calmer evenings for children. | Fewer disruptions to routines and sleep. | Strength | No
| Staffing | Evening staffing relies on agency cover more than the team would like. | Regulation 44 reports; staff feedback | Children see more unfamiliar faces at the most sensitive time of day. | May affect consistency of support. | Area for improvement | Yes | Yes
| Children's experiences | Children want more involvement in planning weekend activities. | Children's meetings | Children feel weekend decisions are made for them. | Opportunity to build ownership and independence. | Area for improvement | Yes | Yes
| Education | One education placement remains fragile despite improved attendance overall. | Attendance themes; school feedback | Uncertainty for the child concerned. | Risk to continuity of learning. | Further review required | Yes | Yes
| Health | All routine health checks are complete; one dental appointment is outstanding. | Health outcomes |  |  | Strength | No

## ACTIONS
FICTIONAL EXAMPLE — FOR DEMONSTRATION ONLY
REGULATION 45 REVIEW TOOLKIT | [8 empty] | ← Dashboard
Improvement Actions
Give every action an owner and a due date. The Status column works itself out — overdue and due-soon actions also surface on the Dashboard.
Action ID | Source / Finding ID | Action | Responsible role | Date created | Due date | Progress | Completion date | Outcome / completion note | Status
| F-003 | Review evening staffing arrangements and agency use with the provider | Registered Manager |  |  | In progress
| F-004 | Introduce a children's weekend activity planning meeting | Deputy Manager |  |  | In progress
| F-005 | Arrange an education planning meeting with the school and placing authority | Registered Manager |  |  | Not started
| F-006 | Book the outstanding dental appointment | Deputy Manager | 2026-07-10 | 2026-07-24 | Complete | 2026-07-20 | Appointment attended 20 July.
Formulas:
Status = IF([Action]="","",IF([Progress]="Complete","Completed",IF([Progress]="No longer required","Closed",IF([Due date]="","No due date",IF([Due date]<TODAY(),"Overdue",IF([Due date]-TODAY()<=14,"Due soon","On track"))))))

## REPORT
FICTIONAL EXAMPLE — FOR DEMONSTRATION ONLY
REGULATION 45 REVIEW TOOLKIT |  | ← Dashboard
Regulation 45 Quality of Care Review
Report preparation workspace. Sections marked “pulled from” update automatically; the rest is yours to write. Print or export to PDF when ready.
Children's home
Ofsted URN
Provider
Review period
Review lead
Date completed
REPORT PREPARATION CHECKS
Review period entered
Evidence reviewed
Stakeholder views considered
Findings recorded
Improvement actions considered
Completion date entered
1. Review overview
Summarise the review in your own words — scope, headline picture, anything a reader should know first.
2. How the review was conducted
Describe the evidence and methods considered. The EVIDENCE sheet is your index.
3. Children's experiences
Pulled from FINDINGS — the “Children's experience / impact” notes. Add your narrative below.
4. Outcomes and development
Pulled from FINDINGS — the “Outcomes / development impact” notes. Add your narrative below.
5. Views considered
Coverage is pulled from VIEWS. Summarise the themes from each group below.
6. What is working well
Pulled from FINDINGS classified as Strength. Review and edit your narrative below.
7. Areas for improvement
Pulled from FINDINGS classified as Area for improvement.
8. Matters requiring further review
Pulled from FINDINGS classified as Further review required.
9. Improvement action plan
Open actions pulled from ACTIONS. Completed actions stay on the ACTIONS sheet as the audit trail.
10. Final management summary
Your closing summary — overall position, priorities for the next period, anything for the Responsible Individual.
Prepared with the Regulation 45 Review Toolkit — an independent management-support resource, not produced or endorsed by Ofsted.

## LISTS (hidden)
Roles | YesNo | ReviewAreas | PlanStatus | EvidenceCategories | EvidenceSources | StakeholderGroups | ViewMethods | ViewClassifications | FindingClassifications | ActionProgress | Validation lists for the workbook's dropdowns. Hidden in the released file; unhide via Home → Format → Hide & Unhide if you need to inspect it.
Registered Manager | Yes | Children's experiences | Not started | Quality Assurance | Regulation 44 reports | Children | Children's meeting | Positive theme | Strength | Not started
Deputy Manager | No | Outcomes | In progress | Children's Experiences | Previous Regulation 45 review | Parents / Carers | Key-work discussion | Improvement theme | Area for improvement | In progress
Responsible Individual |  | Safeguarding | Reviewed | Safeguarding | Previous Regulation 45 action plan | Placing Authorities / Professionals | Survey | Mixed | Further review required | Complete
Owner / Director |  | Behaviour / support | Follow-up required | Behaviour / Support | Ofsted inspection findings | Staff | Advocacy | Information only |  | No longer required
Operations Manager |  | Education |  | Health | Internal audits |  | Individual feedback
Quality / Compliance |  | Health |  | Education | Statement of Purpose review |  | Meeting
Other |  | Relationships |  | Staffing | Location assessment / review |  | Telephone feedback
|  | Activities |  | Other | Children's meetings |  | Email feedback
|  | Family / contact |  |  | Individual feedback themes |  | Placement review
|  | Staffing |  |  | Complaints |  | Professional feedback
|  | Leadership |  |  | Compliments |  | Team meeting
|  | Complaints |  |  | Advocacy themes |  | Supervision themes
|  | Environment |  |  | Key-work themes |  | Workshop
|  | Previous improvement actions |  |  | Safeguarding themes |  | Other
|  | Other |  |  | Missing-from-care themes
Serious incidents
Regulation 40 notifications
Incident trends
Restraint / restrictive-practice trends
Behaviour-support reviews
Health outcomes
Medication themes
Access to health services
Attendance themes
Education progress
PEP-related themes
School / college feedback
Staffing stability
Vacancies
Agency use
Training
Supervision
Competency
Recruitment themes
Other